## Assessed_projects
Projects ranking model
|  |  | Project name: | project 1 | project 2 | project 3 | project 4
0 = not acceptable; 1 = poor; 2 = sufficient; 3 = good; 4 = first-rate | Average | Mode | PM: | PM-1 | PM-2 | PM-3 | PM-4
Context of the project (looking at the big picture is still a relevant issue for almost any PM) | 2.3929 | 3 |  | 2.4286 | 2.7143 | 2.1429 | 2.2857
Project goals, needs and expected benefits (understand, clearly state and agree with customer direct project goals, needs to satisfy and contribute to the customer's business) | 2.25 | 2 |  | 2 | 3 | 2 | 2
Project Stakeholders influence map (understand the interests of the different stakeholders and be proactive in mitigate stakeholders' activities that might adversely affect the project) | 2.5 | 3 |  | 3 | 3 | 2 | 2
Customer involvement (obtain the customer is directly involved in the project, consciously taking the appropriate responsibilities sponsor, users / user champions) | 2.5 | 3 |  | 3 | 2 | 2 | 3
Project team involvement (facilitate/encourage others, making them feel strong and a true contributor to overall project success; when possible, include customer's resource in the project team) | 3 | 3 |  | 3 | 3 | 3 | 3
Management involvement (be sure the appropriate level of management is properly informed and assure the right level of support) |  |  |  | 3 | 3 | 3 | 3
Link with other projects and processes (view the project not as a "stand-alone" endeavor, but strive to understand and to take in consideration all the identifiable links with the surrounding organizational environment) | 1.5 | 1 |  | 1 | 3 | 1 | 1
Customer expectations management (pay great attention to generate the expectations consciously and to perform consequently; avoid to say "yes", thinking "not") | 2 | 2 |  | 2 | 2 | 2 | 2
Project Definition (without a consistent scope management there is no route for project success) | 2.375 | 3 |  | 2.5 | 2.5 | 2.1667 | 2.3333
Project Objectives (triple constraint & identify and agree with relevant stakeholders the project driver) | 2.25 | 2 |  | 2 | 3 | 2 | 2
Project Requirements (functional / not functional; evaluating the degree of completeness and accuracy of requirements definition and make the customer aware of this, verbally and in writing ) | 2.5 | 3 |  | 3 | 2 | 2 | 3
Project Assumptions & Constraints (state all relevant project assumptions, made by us and Customer, and all relevant project constraints. Assumptions usually imply risks while constraints limit the team's options regarding the project) | 1.25 | 1 |  | 1 | 2 | 1 | 1
Technical solution (Although technical solution is not part of project management processes, we need to be sure that the product of the project is defined before to plan the project itself. Technical solution may be detailed or high level, depending on the circumstances. In any case, technical solution must fit project requirements plus assumptions and constraints) | 3 | 3 |  | 3 | 3 | 3 | 3
Project Deliverables (second / third WBS level; describe all relevant project deliverables that fit contract obligation and/or make the progress of the project visible to the customer) | 3 | 3 |  | 3 | 3 | 3 | 3
Acceptance Criteria (for each deliverable, state clearly and accurately the criteria basing on which customer will accept the deliverable. Acceptance Criteria are the basis for test plan development and execution) | 2.25 | 2 |  | 3 | 2 | 2 | 2
Project Planning (a consistent Project Plan allows project simulation and uncertainties reduction) | 1.9062 | 1 |  | 2 | 2.5 | 1.625 | 1.5
Milestone (clearly identify and document contractual milestones, distinguish them from the internal ones; if the contract includes a final delivery only, agree with customer some intermediate milestones) | 2.75 | 3 |  | 3 | 3 | 3 | 2
External Dependencies (clearly identify and document all relevant external dependencies, distinguishing those related to customer from those originated by subcontractors; external dependencies is a very good way to concretely involve the customer inside the project) | 1 | 1 |  | 1 | 1 | 1 | 1
Project Schedule (usually represented by a Gantt chart, where duration is based on effort/resources; the Gantt must include milestones and external dependencies and must reflect assumptions and constraints) | 2.5 | 3 |  | 3 | 3 | 2 | 2
Resource Estimation (may be a view of the Gantt, specifying for each resource type, internal and external, total estimated effort and timeframe. This is input to resource managers, and must be based on documented assumptions and known constraints) | 2.5 | 3 |  | 3 | 3 | 2 | 2
Role & Responsibility (specify for both us and Customer participants to the project what is expected to do, who is accountable for, and the decision and escalation processes) | 2.25 | 2 |  | 3 | 2 | 2 | 2
Cost Estimation (based on effort estimate for labor costs, based on suppliers' proposal for non labor costs) | 1.5 | 1 |  | 1 | 3 | 1 | 1
Prerequisites (specify what the project team needs in order to reach project success, considering the known constraints and, of course, respecting projects objectives and requirements) | 1.5 | 1 |  | 1 | 3 | 1 | 1
Project Risks (identify, analyze, evaluate and respond to project risks, adopting a structured approach based on best practices; be sure management is aware of project risks and, when applicable, discuss project risks with customer) | 1.25 | 1 |  | 1 | 2 | 1 | 1
SOW / Project Proposal (Good proposal and good contract state the right conditions for success) | 2.25 | 2 |  | 2 | 3 | 2 | 2
SOW checklist compliance (see Project SOW Checklist, where for: < 50% = 0; from 50 to 70% = 1; from 71 to 80 = 2; from 81 to 90 = 3; > 90 = 4) | 2.25 | 2 |  | 2 | 3 | 2 | 2
SOW management process compliance (see SOW management process) | 2.25 | 2 |  | 2 | 3 | 2 | 2
Project Execution & Control (once defined, planned and agreed, the project needs to be managed on daily basis) | 2 | 2 |  | 2 | 2.1667 | 2 | 1.8333
Suppliers Management (control suppliers' performance on regular basis, report any inconsistencies and administer the contract) | 1.5 | 1 |  | 1 | 3 | 1 | 1
Actual resources availability (monitoring actual resource availability compared with the plan and directly manage discrepancies or escalate the problem to appropriate organization level) | 2 | 2 |  | 2 | 2 | 2 | 2
Project performance reporting (prepare and issue the status report on regular basis; do not limit to report what already happened but focus on estimation to complete and all possible preventive / corrective actions needed to project success) | 1.5 | 2 |  | 2 | 2 | 1 | 1
Issue management (promptly update the OIL and share issues with appropriate stakeholders; be proactive in monitoring corrective actions and maintain the final accountability of them) | 2 | 2 |  | 2 | 2 | 2 | 2
Change Control (manage project changes applying change control procedure specified in SOW for relevant changes and track any minor changes in status report; do not perform changes automatically, simply on customer request basis) | 2.5 | 2 |  | 2 | 3 | 3 | 2
Formal Acceptance (assure customer formally accept in writing and with signature project deliverables, ad interim and final, applying the acceptance criteria previously defined and agreed) | 2.5 | 3 |  | 3 | 1 | 3 | 3
At Portfolio / Project level | 2.1338 | 2 |  | 2.197 | 2.5202 | 2.2418 | 1.9596